## Cost Estimate
Rankin Inlet, Arviat & Chesterfield Inlet — NWI Last Mile Wireless System
Mock Cost Estimate by WBS — 3-Community / 50-Subscriber Solution
Prepared by: Northern Wireless Inc. (NWI) ¦ Reference: NWI-EST-RANKIN-2026 Rev 0 ¦ Basis: WBSWithEstimatesV1.xlsx + Scope of Supply Summary
WBS No | Item | Unit | Qty | Unit Price | Our Cost Total | Cust Cost Total | Profit | Std. Delivery (Cal. Days) | Effort (Hrs) | Notes / Source Mapping
Engineering & Admin
E-SVT | Site visit (2 days) | Each | 1 | 1400 | 1400 | 1820 | 420 | 2 | 16 | Site study & conceptual design — kickoff site visit
E-SST | Site study | Days | 1 | 2000 | 2000 | 2600 | 600 | 5 | 40 | Site study & conceptual design
E-SLD | Site layout drawing | Days | 1 | 800 | 800 | 1040 | 240 | 2 | 16 | Layout drawing and BOM
E-NDD | Network design and drawing | Days | 1 | 1200 | 1200 | 1560 | 360 | 3 | 24 | Network design and configuration drawings
E-TMN | Technical/Training Manual | Days | 1 | 2000 | 2000 | 2600 | 600 | 5 | 40 | Training manual documentation
E-BDS | Engineering — Base Station subsystem | Days | 1 | 1200 | 1200 | 1560 | 360 | 3 | 24 | Coordination — base station (Bandwidth Distribution System) engineering
E-BCS | Engineering — Wired Network subsystem | Days | 1 | 1600 | 1600 | 2080 | 480 | 4 | 32 | Coordination — wired network / bandwidth control gateway engineering
E-CPE | Engineering — Premise Equipment subsystem | Days | 1 | 400 | 400 | 520 | 120 | 1 | 8 | Coordination — CPE configuration template for 50 units
PM-COORD* | Project Management & Coordination | Days | 1 | 1600 | 1600 | 2080 | 480 | 4 | 32 | *By analogy at WBS $400/day rate (no dedicated WBS row); oversees engineering-to-startup handoff
PROC* | Procurement / Purchasing Support | Days | 1 | 800 | 800 | 1040 | 240 | 2 | 16 | *Matches Sample Cost Template 'Procurement time' line (2 days / $800)
| Subtotal — Engineering & Admin |  |  |  | 13000 | 16900 | 3900 | 5 | 248
Base Station
C-BDS-APC | Access Point Cabinet | Each | 1 | 2200 | 2200 | 2860 | 660 | 21 |  | 1 – Access point & cabinet
C-BDS-WAP | Wireless Access Point / Radio Card | Each | 2 | 2200 | 4400 | 5720 | 1320 | 21 |  | 2 – Radio Card (AP radio modules)
C-BDS-ANT | Omni Antenna | Each | 2 | 600 | 1200 | 1560 | 360 | 14 |  | 2 – Antennas/Amplifier (antenna side)
C-BDS-AMP | Bi-Directional Amplifier | Each | 2 | 800 | 1600 | 2080 | 480 | 14 |  | 2 – Antennas/Amplifier (amplifier side)
C-BDS-CBL | Cable Coax | Each | 2 | 150 | 300 | 390 | 90 | 7 |  | 2 – Cabling and connectors (cable)
C-BDS-CON | Connectors | Each | 2 | 100 | 200 | 260 | 60 | 7 |  | 2 – Cabling and connectors (connectors)
C-BDS-LGP | Lightning Protection | Each | 1 | 150 | 150 | 195 | 45 | 10 |  | Power outage protection and power conditioning
C-BDS-POE | Power Over Ethernet / Conditioning | Each | 1 | 200 | 200 | 260 | 60 | 10 |  | Power outage protection and power conditioning
C-BRK-ASY | Mast Mounting Bracket Assembly | Each | 1 | 180 | 180 | 234 | 54 | 3 | 4 | Exclusions: NWI supplies bracket to mount antennas to mast (no full tower in this scope)
I-BDS | Install — Base Station | Each | 1 | 800 | 800 | 1040 | 240 | 2 | 16 | Installation of equipment (base station)
S-BDS | Startup — Base Station | Each | 1 | 400 | 400 | 520 | 120 | 1 | 8 | On-the-ground / installed on-site testing (base station)
| Subtotal — Base Station |  |  |  | 11630 | 15119 | 3489 | 21 | 28
Wired Network
C-BCS-CHW | Bandwidth Control Gateway — Hardware | Each | 1 | 4000 | 4000 | 5200 | 1200 | 21 |  | Bandwidth control gateway
C-BCS-CSW | Bandwidth Control Gateway — Software | Each | 1 | 1500 | 1500 | 1950 | 450 | 14 |  | Bandwidth control gateway
C-BCS-CBL | Cable — Wired Network | Each | 1 | 300 | 300 | 390 | 90 | 10 |  | Wired network cabling
C-BSS-RTR | Router / Main Hub-Switch | Each | 1 | 2500 | 2500 | 3250 | 750 | 21 |  | Main Hub/switch
C-BCS-LGP* | Power Outage Protection & Conditioning | Each | 1 | 150 | 150 | 195 | 45 | 10 |  | *Wired network side; cost by analogy to C-BDS-LGP (no dedicated WBS row)
I-BCS | Install — Wired Network | Each | 1 | 2000 | 2000 | 2600 | 600 | 3 | 24 | Installation of equipment / configuration (wired network)
S-BCS | Startup — Wired Network | Each | 1 | 800 | 800 | 1040 | 240 | 2 | 16 | On-the-ground / installed on-site testing (wired network)
| Subtotal — Wired Network |  |  |  | 11250 | 14625 | 3375 | 21 | 40
Premise Equipment (Qty 50 Subscribers)
C-CPE-CWD | Modem/Radio (Wireless Device) | Each | 50 | 175 | 8750 | 11375 | 2625 | 14 |  | 50 – Modem/Radio
C-CPE-ANT | Patch Antenna | Each | 50 | 25 | 1250 | 1625 | 375 | 14 |  | 50 – Patch Antenna
C-CPE-CBL | RF Cable with Connectors | Each | 50 | 8 | 400 | 520 | 120 | 7 |  | 50 – RF Cable with Connectors
C-CPE-BRK | Mounting Bracket | Each | 50 | 15 | 750 | 975 | 225 | 7 |  | Premise antenna mounting hardware
CPE-ETH* | Ethernet Cable & RJ45 Connectors | Each | 50 | 6 | 300 | 390 | 90 | 7 |  | *50 – Ethernet cable and RJ45 connectors; estimated by analogy (no dedicated WBS row)
I-CPE | Install — Premise Equipment | Each | 50 | 300 | 15000 | 19500 | 4500 | 10 | 300 | Installation of equipment (premise); duration is crew-adjusted (2-person crew, ~5 installs/day) — NOT a simple x50 of the WBS per-unit day figure; effort hours (300 = 6 hrs x 50) do scale linearly
S-CPE | Startup — Premise Equipment (batch commissioning) | Each | 1 | 1200 | 1200 | 1560 | 360 | 3 | 24 | Installed on-site testing across all 50 premises (single batch commissioning task)
| Subtotal — Premise Equipment |  |  |  | 27650 | 35945 | 8295 | 14 | 324
Installation & Commissioning — Supporting Items
SFTY-EQP* | Safety Climbing Equipment (rental/consumables) | Each | 1 | 250 | 250 | 325 | 75 | 2 |  | *Safety climbing equipment; estimated by analogy (no dedicated WBS row)
TOOLS-INS* | Installation Tools & Consumables | Each | 1 | 150 | 150 | 195 | 45 | 2 |  | *Tools for installation; estimated by analogy (no dedicated WBS row)
| Subtotal — Installation & Commissioning (Supporting Items) |  |  |  | 400 | 520 | 120 | 2 | 0
Note: per-subsystem install/startup ('installation of equipment', 'on-the-ground / installed on-site testing') costs are itemized within Base Station, Wired Network and Premise Equipment above.
Training
TRN-OJT | On-Site Training (customer personnel, 4-hr course) | Each | 1 | 200 | 200 | 260 | 60 | 1 | 4 | One-time local training course, 4 hours (Scope of Supply — Support Details). Training manual costed under Engineering (E-TMN)
| Subtotal — Training |  |  |  | 200 | 260 | 60 | 1 | 4
Support (2-Month Included Period)
T-WAP | Support — Wireless Access Point | Each | 1 | 200 | 200 | 260 | 60 | 1 | 4 | 24/7 technical support
T-BCU | Support — Bandwidth Control Unit | Each | 1 | 200 | 200 | 260 | 60 | 1 | 4 | 24/7 technical support
T-CSW | Support — Computer Software | Each | 1 | 200 | 200 | 260 | 60 | 1 | 4 | 24/7 technical support
T-RTR | Support — Router | Each | 1 | 200 | 200 | 260 | 60 | 1 | 4 | 24/7 technical support
T-CWD | Support — Customer Wireless Device (fleet) | Each | 1 | 100 | 100 | 130 | 30 | 1 | 2 | 24/7 technical support
T-SPT | Support — General (24/7 coordination + telephone support) | Each | 1 | 400 | 400 | 520 | 120 | 1 | 8 | Two months telephone support and remote administration included
| Subtotal — Support (2-Month Included Period) |  |  |  | 1300 | 1690 | 390 | 1 | 26
| TOTAL — SUPPLY, INSTALL & COMMISSION |  |  |  | 65430 | 85059 | 19629 |  | 670
Assumptions & Methodology
• Source data: costs, unit prices and standard delivery spans are drawn from WBSWithEstimatesV1.xlsx (internal $400/day = $50/hr labor rate); quantities are drawn from ScopeOfSupplySummary-nwi-last-mile-system.md.
• Lines marked with * have no directly corresponding WBS row and are estimated by analogy to the nearest comparable WBS item, consistent with the source workbook's own Assumptions tab methodology.
• Component (hardware/software) 'Std. Delivery' is vendor lead time for the order as a whole and is NOT multiplied by quantity (bulk ordering 2 or 50 units does not take proportionally longer).
• Installation labor (I-CPE) hours DO scale with quantity (6 hrs/unit x 50 = 300 hrs total labor), but the calendar-day duration is crew-adjusted (assumes a 2-person install crew averaging ~5 premises/day) rather than a literal x50 of the single-unit WBS day figure.
• Startup/commissioning (S-*) rows represent a single batch verification task per subsystem, not a per-unit cost, and are held at Qty 1.
• Cust Cost Total = Our Cost Total x 1.30 (30% standard NWI markup); Profit = Cust Cost Total - Our Cost Total. Adjust the markup assumption in column H formulas as needed for a firm quote.
• Excludes: emergency backup power, firewalls, ISP services, spares, full tower/mast structure (bracket-mount only), NIC, and client VPN/encryption configuration — per Scope of Supply Summary Exclusions.
• Figures are mock/ballpark planning estimates only and should be validated against current vendor quotes and labor rates before use in a firm customer quote.

## Raw Data
TBID | tbMDWBS | tbMDPhase | Sub-Project or WorkPackage | tbName | tbBudget | tbDuration | tbWork | tbMDNotes
100 | C-BCS-CBL | Equipment Procurement | Bandwidth Control System | Cable — Wired Network | 300 | 10 | 0 | Wired network cabling
101 | C-BCS-CHW | Equipment Procurement | Bandwidth Control System | Bandwidth Control Gateway — Hardware | 4000 | 21 | 0 | Bandwidth control gateway
102 | C-BCS-CSW | Equipment Procurement | Bandwidth Control System | Bandwidth Control Gateway — Software | 1500 | 14 | 0 | Bandwidth control gateway
103 | C-BCS-LGP* | Equipment Procurement | Bandwidth Control System | Power Outage Protection & Conditioning | 150 | 10 | 0 | *Wired network side; cost by analogy to C-BDS-LGP (no dedicated WBS row)
104 | C-BDS-AMP | Equipment Procurement | Bandwidth Distrubution System | Bi-Directional Amplifier | 1600 | 14 | 0 | 2 – Antennas/Amplifier (amplifier side)
105 | C-BDS-ANT | Equipment Procurement | Bandwidth Distrubution System | Omni Antenna | 1200 | 14 | 0 | 2 – Antennas/Amplifier (antenna side)
106 | C-BDS-APC | Equipment Procurement | Bandwidth Distrubution System | Access Point Cabinet | 2200 | 21 | 0 | 1 – Access point & cabinet
107 | C-BDS-CBL | Equipment Procurement | Bandwidth Distrubution System | Cable Coax | 300 | 7 | 0 | 2 – Cabling and connectors (cable)
108 | C-BDS-CON | Equipment Procurement | Bandwidth Distrubution System | Connectors | 200 | 7 | 0 | 2 – Cabling and connectors (connectors)
109 | C-BDS-LGP | Equipment Procurement | Bandwidth Distrubution System | Lightning Protection | 150 | 10 | 0 | Power outage protection and power conditioning
110 | C-BDS-POE | Equipment Procurement | Bandwidth Distrubution System | Power Over Ethernet / Conditioning | 200 | 10 | 0 | Power outage protection and power conditioning
111 | C-BDS-WAP | Equipment Procurement | Bandwidth Distrubution System | Wireless Access Point / Radio Card | 4400 | 21 | 0 | 2 – Radio Card (AP radio modules)
112 | C-BSS-RTR | Equipment Procurement | Bandwidth Supply system | Router / Main Hub-Switch | 2500 | 21 | 0 | Main Hub/switch
113 | C-CPE-ANT | Equipment Procurement | Customer Premise Equipment | Patch Antenna | 1250 | 14 | 0 | 50 – Patch Antenna
114 | C-CPE-BRK | Equipment Procurement | Customer Premise Equipment | Mounting Bracket | 750 | 7 | 0 | Premise antenna mounting hardware
115 | C-CPE-CBL | Equipment Procurement | Customer Premise Equipment | RF Cable with Connectors | 400 | 7 | 0 | 50 – RF Cable with Connectors
116 | C-CPE-CWD | Equipment Procurement | Customer Premise Equipment | Modem/Radio (Wireless Device) | 8750 | 14 | 0 | 50 – Modem/Radio
117 | E-BCS | Engineerring | Engineering - Bandwidth Control System | Engineering — Wired Network subsystem | 1600 | 4 | 32 | Coordination — wired network / bandwidth control gateway engineering
118 | E-BDS | Engineerring | Engineering - Bandwidth Distrubution System | Engineering — Base Station subsystem | 1200 | 5 | 24 | Coordination — base station (Bandwidth Distribution System) engineering
119 | E-CPE | Engineerring | Engineering - Customer Premise Equipment | Engineering — Premise Equipment subsystem | 400 | 5 | 8 | Coordination — CPE configuration template for 50 units
121 | I-BCS | Installation | Install - Bandwidth Control System | Install — Wired Network | 2000 | 6 | 24 | Installation of equipment / configuration (wired network)
122 | I-BDS | Installation | Install - Bandwidth Distrubution System | Install — Base Station | 800 | 5 | 16 | Installation of equipment (base station)
123 | I-CPE | Installation | Install - Customer Premise Equipment | Install — Premise Equipment | 15000 | 10 | 300 | Installation of equipment (premise); duration is crew-adjusted (2-person crew, ~5 installs/day) — NOT a simple x50 of the WBS per-unit day figure; effort hours (300 = 6 hrs x 50) do scale linearly
124 | E-NDD | Engineerring | Network design and drawing | Network design and drawing | 1200 | 3 | 24 | Network design and configuration drawings
125 | E-SLD | Engineerring | Site layout drawing | Site layout drawing | 800 | 7 | 16 | Layout drawing and BOM
126 | E-SST | Engineerring | Site study | Site study | 2000 | 5 | 40 | Site study & conceptual design
127 | E-SVT | Engineerring | Site visit 2 days | Site visit (2 days) | 1400 | 2 | 16 | Site study & conceptual design — kickoff site visit
128 | S-BCS | Startup | Startup - Bandwidth Control System | Startup — Wired Network | 800 | 4 | 16 | On-the-ground / installed on-site testing (wired network)
129 | S-BDS | Startup | Startup - Bandwidth Distrubution System | Startup — Base Station | 400 | 10 | 8 | On-the-ground / installed on-site testing (base station)
130 | S-CPE | Startup | Startup - Customer Premise Equipment | Startup — Premise Equipment (batch commissioning) | 1200 | 20 | 24 | Installed on-site testing across all 50 premises (single batch commissioning task)
131 | T-BCU | Support | Support - Bandwidth Control Unit | Support — Bandwidth Control Unit | 200 | 20 | 4 | 24/7 technical support
132 | T-CSW | Support | Support - Computer Software | Support — Computer Software | 200 | 20 | 4 | 24/7 technical support
133 | T-CWD | Support | Support - Customer Wireless Device | Support — Customer Wireless Device (fleet) | 100 | 20 | 2 | 24/7 technical support
134 | T-SPT | Support | Support - General Support | Support — General (24/7 coordination + telephone support) | 400 | 20 | 8 | Two months telephone support and remote administration included
135 | T-RTR | Support | Support - Router | Support — Router | 200 | 20 | 4 | 24/7 technical support
136 | T-WAP | Support | Support - Wireless Access Point | Support — Wireless Access Point | 200 | 20 | 4 | 24/7 technical support
137 | E-TMN | Engineerring | Technical Manual | Technical/Training Manual | 2000 | 5 | 40 | Training manual documentation
20

## WBSNew
L1 | L2 | L3 | WBS No | WBSTitle | Standard Cost | Standard Delivery in Calendar Days | Effort/Hours
C |  |  |  | Components
C | BBS |  | C-BBS | Bandwidth Backhaul System | 4300 | 21
C | BBS | ANT | C-BBS-ANT | Antenna - Bandwidth Backhaul System | 4000 | 21
C | BBS | CBL | C-BBS-CBL | Cable Coax - Bandwidth Backhaul System | 200 | 10
C | BBS | CON | C-BBS-CON | Connectors - Bandwidth Backhaul System | 100 | 7
C | BCS |  | C-BCS | Bandwidth Control System | 5800 | 21
C | BCS | CBL | C-BCS-CBL | Cables - Bandwidth Control System | 300 | 10
C | BCS | CHW | C-BCS-CHW | Computer Hardware - Bandwidth Control System | 4000 | 21
C | BCS | CSW | C-BCS-CSW | Computer SW - Bandwidth Control System | 1500 | 14
C | BDS |  | C-BDS | Bandwidth Distrubution System | 6400 | 21
C | BDS | AMP | C-BDS-AMP | Amplifier - Bandwidth Distrubution System | 800 | 14
C | BDS | ANT | C-BDS-ANT | Antenna - Bandwidth Distrubution System | 600 | 14
C | BDS | APC | C-BDS-APC | Access Point Cabinet - Bandwidth Distrubution System | 2200 | 21
C | BDS | CBL | C-BDS-CBL | Cable - Bandwidth Distrubution System | 150 | 7
C | BDS | CON | C-BDS-CON | Connectors - Bandwidth Distrubution System | 100 | 7
C | BDS | LGP | C-BDS-LGP | Lightning Protectors - Bandwidth Distrubution System | 150 | 10
C | BDS | POE | C-BDS-POE | Power Over Ethernet - Bandwidth Distrubution System | 200 | 10
C | BDS | WAP | C-BDS-WAP | Wireless Access Point - Bandwidth Distrubution System | 2200 | 21
C | BSS |  | C-BSS | Bandwidth Supply system | 10800 | 30
C | BSS | CBL | C-BSS-CBL | Cable - Bandwidth Supply system | 300 | 10
C | BSS | EQB | C-BSS-EQB | Equipment Building - Bandwidth Supply System | 8000 | 30
C | BSS | RTR | C-BSS-RTR | Router - Bandwidth Supply system | 2500 | 21
C | CPE |  | C-CPE | Customer Premise Equipment | 223 | 14
C | CPE | ANT | C-CPE-ANT | Antenna - Customer Premise Equipment | 25 | 14
C | CPE | BRK | C-CPE-BRK | Brackets - Customer Premise Equipment | 15 | 7
C | CPE | CBL | C-CPE-CBL | Cable - Customer Premise Equipment | 8 | 7
C | CPE | CWD | C-CPE-CWD | Wireless Device - Customer Premise Equipment | 175 | 14
C | NSS |  | C-NSS | Network Server System | 5500 | 21
C | NSS | CHW | C-NSS-CHW | Computer Hardware - Network Server System | 4000 | 21
C | NSS | CSW | C-NSS-CSW | Computer Software - Network Server System | 1500 | 14
C | TWR |  | C-TWR | Tower System | 14700 | 30
C | TWR | FRM | C-TWR-FRM | Tower Frame - Tower System | 6000 | 30
C | TWR | BLD | C-TWR-BLD | Building - Tower System | 4000 | 30
C | TWR | BRK | C-TWR-BRK | Brackets - Tower System | 200 | 10
C | TWR | FDN | C-TWR-FDN | Foundaton - Tower System | 3000 | 21
C | TWR | FEN | C-TWR-FEN | Fence - Tower System | 1500 | 14
C | UCS |  | C-UCS | Unified Communication System | 12850 | 21
C | UCS | CBL | C-UCS-CBL | Cable - Unified Communication System | 200 | 10
C | UCS | CHW | C-UCS-CHW | Computer Hardware - Unified Communication System | 2500 | 21
C | UCS | CSW | C-UCS-CSW | Computer SW - Unified Communication System | 3000 | 14
C | UCS | PBX | C-UCS-PBX | Private Branch Exchange - Unified Communication System | 5000 | 21
C | UCS | RTR | C-UCS-RTR | Router - Unified Communication System | 1200 | 14
C | UCS | SIP | C-UCS-SIP | SIP Trunk - Unified Communication System | 800 | 7
C | UCS | SPH | C-UCS-SPH | Smart Phone - Unified Communication System | 150 | 7
C | BRK | ASY | C-BRK-ASY | Assembly - Brackets | 180 | 3 | 4
C | CAB | ASY | C-CAB-ASY | Assembly - Cabinet | 420 | 3 | 8
C | CBL | ASY | C-CBL-ASY | Assembly - Coax Cable | 240 | 2 | 5
E |  |  | E | Engineering
E | ENG |  | E-BBS | Engineering Bandwidth Backhaul System | 1200 | 3 | 24
E | ENG |  | E-BCS | Engineering - Bandwidth Control System | 1600 | 4 | 32
E | ENG |  | E-BDS | Engineering - Bandwidth Distrubution System | 1200 | 3 | 24
E | ENG |  | E-BSS | Engineering - Bandwidth Supply system | 800 | 2 | 16
E | ENG |  | E-CPE | Engineering - Customer Premise Equipment | 400 | 1 | 8
E | ENG |  | E-NSS | Engineering - Network Server System | 1200 | 3 | 24
E | ENG |  | E-TWR | Engineering - Tower System | 800 | 2 | 16
E | ENG |  | E-UCS | Engineering - Unified Communication System | 1200 | 3 | 24
E | ENG |  | E-SVT | Site visit 2 days | 1400 | 2 | 16
E | ENG |  | E-SST | Site study | 2000 | 5 | 40
E | ENG |  | E-SLD | Site layout drawing | 800 | 2 | 16
E | ENG |  | E-NDD | Network design and drawing | 1200 | 3 | 24
E | ENG |  | E-TMN | Technical Manual | 2000 | 5 | 40
I |  |  |  | Installation
I | INS |  | I-BBS | Install - Bandwidth Backhaul System | 400 | 1 | 8
I | INS |  | I-BCS | Install - Bandwidth Control System | 2000 | 3 | 24
I | INS |  | I-BDS | Install - Bandwidth Distrubution System | 800 | 2 | 16
I | INS |  | I-BSS | Install - Bandwidth Supply System | 2000 | 3 | 24
I | INS |  | I-CPE | Install - Customer Premise Equipment | 300 | 1 | 6
I | INS |  | I-NSS | Install - Network Server System | 2000 | 2 | 16
I | INS |  | I-TWR | Install - Tower System | 2000 | 1 | 8
I | INS |  | I-UCS | Install - Unified Communication System | 1000 | 2 | 16
S |  |  |  | Start-up
S | STP |  | S-BBS | Startup - Bandwidth Backhaul System | 400 | 1 | 8
S | STP |  | S-BCS | Startup - Bandwidth Control System | 800 | 2 | 16
S | STP |  | S-BDS | Startup - Bandwidth Distrubution System | 400 | 1 | 8
S | STP |  | S-BSS | Startup - Bandwidth Supply system | 400 | 1 | 8
S | STP |  | S-CPE | Startup - Customer Premise Equipment | 1200 | 3 | 24
S | STP |  | S-NSS | Startup - Network Server System | 800 | 2 | 16
S | STP |  | S-TWR | Startup - Tower System | 400 | 1 | 8
S | STP |  | S-UCS | Startup - Unified Communication System | 800 | 2 | 16
T |  |  |  | Toubleshooting
T | BCU |  |  | Bandwidth Control Unit
T | SPT |  | T-BCU | Support - Bandwidth Control Unit | 200 | 1 | 4
T | CSW |  |  | Computer Software
T | SPT |  | T-CSW | Support - Computer Software | 200 | 1 | 4
T | CWD |  |  | Customer Wireless Device
T | SPT |  | T-CWD | Support - Customer Wireless Device | 100 | 1 | 2
T | RTR |  |  | Router
T | SPT |  | T-RTR | Support - Router | 200 | 1 | 4
T | SPT |  |  | General Support
T | SPT |  | T-SPT | Support - General Support | 400 | 1 | 8
T | WAP |  |  | Wireless Access Point
T | SPT |  | T-WAP | Support - Wireless Access Point | 200 | 1 | 4